## Dashboard
Project Management DashBoard |  |  |  |  | 17-Feb-20 to 13-Mar-20
Project | Task | Manager | Start Date | End Date | Days completed | Progress | Duration | Actual | Budget
A | Task 1 | McFay | 2020-02-28 | 2020-03-10 | 3 | 37.5% |  | 32256 | 96000
| Task 2 | Wood | 2020-03-02 | 2020-03-12 | 4 | 44.44% | 9 | 226233 | 513000
| Task 3 | Ladd | 2020-02-20 | 2020-02-26 | 3 | 60% | 5 | 401579 | 616000
| Task 4 | Hirsch | 2020-02-19 | 2020-02-21 | 3 | 100% | 3 | 807069 | 817000
| Task 5 | Samora | 2020-02-21 | 2020-03-02 | 3 | 42.86% | 7 | 173166 | 372000
| Task 6 | McFay | 2020-02-24 | 2020-03-06 | 2 | 20% | 10 | 8400 | 50000
| Task 7 | Wood | 2020-02-24 | 2020-03-06 | 3 | 30% | 10 | 262679 | 807000
| Task 8 | Ladd | 2020-02-24 | 2020-02-26 | 0 | 0% | 3 | 0 | 691000
B | Task 1 | Hirsch | 2020-03-02 | 2020-03-12 | 8 | 88.89% | 9 | 727188 | 787000
| Task 2 | Samora | 2020-03-02 | 2020-03-13 | 2 | 20% | 10 | 47880 | 228000
| Task 3 | McFay | 2020-02-17 | 2020-02-20 | 0 | 0% | 4 | 0 | 147000
| Task 4 | Wood | 2020-02-19 | 2020-02-28 | 5 | 62.5% | 8 | 205123 | 338000
| Task 5 | Ladd | 2020-02-24 | 2020-03-06 | 3 | 30% | 10 | 305949 | 857000
| Task 6 | Hirsch | 2020-02-25 | 2020-03-03 | 3 | 50% | 6 | 322371 | 602000
| Task 7 | Samora | 2020-02-25 | 2020-02-28 | 2 | 50% | 4 | 451440 | 990000
C | Task 1 | Hirsch | 2020-02-17 | 2020-02-21 | 2 | 40% | 5 | 97337 | 218000
| Task 10 | Ladd | 2020-02-24 | 2020-03-02 | 3 | 50% | 6 | 175015 | 416000
| Task 2 | Samora | 2020-02-17 | 2020-02-24 | 3 | 50% | 6 | 177440 | 393000
| Task 3 | McFay | 2020-02-18 | 2020-03-02 | 4 | 40% | 10 | 31046 | 86000
| Task 4 | Wood | 2020-02-21 | 2020-03-04 | 3 | 33.33% | 9 | 261324 | 732000
| Task 5 | Ladd | 2020-02-17 | 2020-02-20 | 1 | 25% | 4 | 116850 | 492000
| Task 6 | Hirsch | 2020-02-20 | 2020-02-27 | 0 | 0% | 6 | 0 | 188000
| Task 7 | Samora | 2020-02-20 | 2020-02-28 | 3 | 42.86% | 7 | 79380 | 180000
| Task 8 | McFay | 2020-02-24 | 2020-02-28 | 2 | 40% | 5 | 195231 | 582000
| Task 9 | Wood | 2020-02-24 | 2020-03-05 | 1 | 11.11% | 9 | 74746 | 562000
D | Task 1 | Hirsch | 2020-02-18 | 2020-02-26 | 7 | 100% | 7 | 273001 | 293000
| Task 10 | Ladd | 2020-02-17 | 2020-02-19 | 3 | 100% | 3 | 64987 | 68000
| Task 2 | Samora | 2020-02-17 | 2020-02-27 | 4 | 44.44% | 9 | 57910 | 224000
| Task 3 | McFay | 2020-02-18 | 2020-02-27 | 0 | 0% | 8 | 0 | 978000
| Task 4 | Wood | 2020-02-20 | 2020-02-28 | 3 | 42.86% | 7 | 379157 | 932000
| Task 5 | Ladd | 2020-02-21 | 2020-02-26 | 1 | 25% | 4 | 322812 | 854000
| Task 6 | Hirsch | 2020-02-21 | 2020-02-28 | 3 | 50% | 6 | 38461 | 81000
| Task 7 | Samora | 2020-02-24 | 2020-03-02 | 5 | 83.33% | 6 | 136468 | 169000
| Task 8 | McFay | 2020-02-25 | 2020-02-28 | 1 | 25% | 4 | 12078 | 61000
| Task 9 | Wood | 2020-02-27 | 2020-03-06 | 3 | 42.86% | 7 | 273048 | 645000
E | Task 1 | Hirsch | 2020-02-17 | 2020-02-28 | 5 | 50% | 10 | 406974 | 839000
| Task 2 | Samora | 2020-02-21 | 2020-02-27 | 4 | 80% | 5 | 487139 | 729000
| Task 3 | McFay | 2020-02-24 | 2020-03-03 | 3 | 42.86% | 7 | 298186 | 826000
| Task 4 | Wood | 2020-02-26 | 2020-03-05 | 2 | 28.57% | 7 | 280583 | 895000
| Task 5 | Ladd | 2020-02-28 | 2020-03-03 | 2 | 66.67% | 3 | 129785 | 341000
Grand Total | [7 empty] | 8340291 | 19695000
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Data
Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
A | Task 1 | McFay | 2020-02-28 | 8 | 2020-03-10 | 3 | 37.5% | 96000 | 32256
A | Task 2 | Wood | 2020-03-02 | 9 | 2020-03-12 | 4 | 44.44% | 513000 | 226233
A | Task 3 | Ladd | 2020-02-20 | 5 | 2020-02-26 | 3 | 60% | 616000 | 401579
A | Task 4 | Hirsch | 2020-02-19 | 3 | 2020-02-21 | 3 | 100% | 817000 | 807069
A | Task 5 | Samora | 2020-02-21 | 7 | 2020-03-02 | 3 | 42.86% | 372000 | 173166
A | Task 6 | McFay | 2020-02-24 | 10 | 2020-03-06 | 2 | 20% | 50000 | 8400
A | Task 7 | Wood | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 807000 | 262679
A | Task 8 | Ladd | 2020-02-24 | 3 | 2020-02-26 | 0 | 0% | 691000 | 0
B | Task 1 | Hirsch | 2020-03-02 | 9 | 2020-03-12 | 8 | 88.89% | 787000 | 727188
B | Task 2 | Samora | 2020-03-02 | 10 | 2020-03-13 | 2 | 20% | 228000 | 47880
B | Task 3 | McFay | 2020-02-17 | 4 | 2020-02-20 | 0 | 0% | 147000 | 0
B | Task 4 | Wood | 2020-02-19 | 8 | 2020-02-28 | 5 | 62.5% | 338000 | 205123
B | Task 5 | Ladd | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 857000 | 305949
B | Task 6 | Hirsch | 2020-02-25 | 6 | 2020-03-03 | 3 | 50% | 602000 | 322371
B | Task 7 | Samora | 2020-02-25 | 4 | 2020-02-28 | 2 | 50% | 990000 | 451440
C | Task 1 | Hirsch | 2020-02-17 | 5 | 2020-02-21 | 2 | 40% | 218000 | 97337
C | Task 2 | Samora | 2020-02-17 | 6 | 2020-02-24 | 3 | 50% | 393000 | 177440
C | Task 3 | McFay | 2020-02-18 | 10 | 2020-03-02 | 4 | 40% | 86000 | 31046
C | Task 4 | Wood | 2020-02-21 | 9 | 2020-03-04 | 3 | 33.33% | 732000 | 261324
C | Task 5 | Ladd | 2020-02-17 | 4 | 2020-02-20 | 1 | 25% | 492000 | 116850
C | Task 6 | Hirsch | 2020-02-20 | 6 | 2020-02-27 | 0 | 0% | 188000 | 0
C | Task 7 | Samora | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 180000 | 79380
C | Task 8 | McFay | 2020-02-24 | 5 | 2020-02-28 | 2 | 40% | 582000 | 195231
C | Task 9 | Wood | 2020-02-24 | 9 | 2020-03-05 | 1 | 11.11% | 562000 | 74746
C | Task 10 | Ladd | 2020-02-24 | 6 | 2020-03-02 | 3 | 50% | 416000 | 175015
D | Task 1 | Hirsch | 2020-02-18 | 7 | 2020-02-26 | 7 | 100% | 293000 | 273001
D | Task 2 | Samora | 2020-02-17 | 9 | 2020-02-27 | 4 | 44.44% | 224000 | 57910
D | Task 3 | McFay | 2020-02-18 | 8 | 2020-02-27 | 0 | 0% | 978000 | 0
D | Task 4 | Wood | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 932000 | 379157
D | Task 5 | Ladd | 2020-02-21 | 4 | 2020-02-26 | 1 | 25% | 854000 | 322812
D | Task 6 | Hirsch | 2020-02-21 | 6 | 2020-02-28 | 3 | 50% | 81000 | 38461
D | Task 7 | Samora | 2020-02-24 | 6 | 2020-03-02 | 5 | 83.33% | 169000 | 136468
D | Task 8 | McFay | 2020-02-25 | 4 | 2020-02-28 | 1 | 25% | 61000 | 12078
D | Task 9 | Wood | 2020-02-27 | 7 | 2020-03-06 | 3 | 42.86% | 645000 | 273048
D | Task 10 | Ladd | 2020-02-17 | 3 | 2020-02-19 | 3 | 100% | 68000 | 64987
E | Task 1 | Hirsch | 2020-02-17 | 10 | 2020-02-28 | 5 | 50% | 839000 | 406974
E | Task 2 | Samora | 2020-02-21 | 5 | 2020-02-27 | 4 | 80% | 729000 | 487139
E | Task 3 | McFay | 2020-02-24 | 7 | 2020-03-03 | 3 | 42.86% | 826000 | 298186
E | Task 4 | Wood | 2020-02-26 | 7 | 2020-03-05 | 2 | 28.57% | 895000 | 280583
E | Task 5 | Ladd | 2020-02-28 | 3 | 2020-03-03 | 2 | 66.67% | 341000 | 129785
Formulas:
End Date = WORKDAY.INTL(Table1[[#This Row],[Start Date]]-1,Table1[[#This Row],[Duration]],1)

## Working
Task Tracker
Not Started | 4 | Values |  |  |  |  | Actual | Budget | Scroll bar
In Progress | 33 | Sum of Days completed | 112 | Days Completed | 42.11% | Bar chart | 8340291 | 19695000 | 16
Completed | 3 | Sum of Duration | 266 | Days Remaining | 57.89% | Doughnut Chart | 42.35% | 57.65%
Remaining | 37
Total Tasks | 40